## Slide 1
VELLORE CITY MUNICIPAL CORPORATION
PROGRESS REPORT AS ON 08.05.2020
UGSS TO VELLORE CITY MUNICIPAL CORPORATION
UNDER AMRUT 2016-17 PHASE II & III

## Slide 2
1 | Name of Scheme | AMRUT – 2016-17 UGSS TO Vellore City Municipal Corporation – Phase II |  |  |  |  |  |  |  |  |  | 
1. | Population and Requirement | Population Benefited (in Lakhs) |  |  |  |  |  |  |  | Sewage in MLD |  | 
 |  | Present (2020) |  | Inter (2035) |  |  | Ultimate (2050) |  |  | Inter (2035) |  | Ultimate (2050)
 |  | 2.62 |  | 3.36 |  |  | 4.33 |  |  | 36.99 |  | 47.70
2 | Administrative Sanction with amount | G.O.(2D) No.52 MA&WS (MC6) dept., dt. 17-08-2017 Rs.343.69Cr.s |  |  |  |  |  |  |  |  |  | 
3 | Technical Sanction with amount | Roc. No. 18281/ 2017/DO1 dt. 17.11.2017 For Package No.1 – Rs. 15100.00 lakh The Chief Engineer Office of Commissioner of Package No.2 – Rs. 17560.00 lakh Municipal Administration, Chennai – 5. Package No.3 – Rs. 6850.00 lakh |  |  |  |  |  |  |  |  |  | 
4 | Date of Work Order | Package 1- Technical Evaluation report placed before ADB for NOC Tender award committee Approved on 18.12.2018 o/o CMA office. LOA issued on 19.12.2018 Work Order Issued on 07.01.2019 |  |  |  | Package 2- Technical Evaluation report placed before ADB for NOC Tender award committee Approved on 18.12.2018 o/o CMA office. LOA issued on 19.12.2018 Work Order Issued on 07.01.2019 |  |  |  |  | Package 3- STP, Technical Evaluation report placed before ADB for NOC Tender award committee Approved on 18.12.2018 o/o CMA office. LOA issued on 19.12.2018 Work Order Issued on 07.01.2019 | 
5 | Agreement No. /date / Value & Period | Agreement No: 1/2018-19 dt 07.01.2019 Rs. 143,73,39,803.42 36 Month |  |  |  | Agreement No: 2/2018-19 dt 07.01.2019 Rs. 163,41,34,304.10 36 Month |  |  |  |  | Agreement No: 3/2018-19 dt 07.01.2019 Rs. 69,71,00,000.00 24 Month | 
6 | Date of Commencement | 07.01.2019 |  |  |  | 07.01.2019 |  |  |  |  | 07.01.2019 | 
7 | Name of the Contractor | M/s SUBAYA CONSTRUCTION COMPANY LTD CHENNAI. |  |  |  | M/s SUBAYA CONSTRUCTION COMPANY LTD CHENNAI. |  |  |  |  | M/s P&C PROJECT PVT LTD CHENNAI | 
8 | Target date for completion | 31.12.2021 |  |  |  | 31.12.2021 |  |  |  |  | 31.12.2020 | 
9 | Expected date for completion | 31.12.2021 |  |  |  | 31.12.2021 |  |  |  |  | 31.12.2020 | 
11 | Description | Grant GOI Cr | GOTN (Cr) |  |  | Own fund (ULB) Cr |  |  | ADB/TUFIDCO/ TNUIFSL loan/grant Cr. |  |  | Total Cr
 | Fund Tie up | 171.84 | 68.74 |  |  | 10.31 |  |  | 92.80 |  |  | 343.69
 | Funds Received | 35.00 |  |  |  | -- |  |  | 7.50 |  |  | 42.50
 | Balance to be received | 205.58 |  |  |  | 10.31 |  |  | 85.30 |  |  | 301.19
 | Budget 2018-19 |  |  |  |  |  |  |  |  |  |  | 
 | Expenditure incurred up to 31.03.2019 | Nil |  |  |  |  |  |  |  |  |  | -
 | Expenditure during 2019-20 | 3286.25 Lakhs |  |  |  |  |  |  |  |  |  | -
 | Cumulative Expenditure as on 08.05.2020 | 3286.25 lakhs |  |  |  |  |  |  |  |  |  | -
12 | Overall Physical Progress (as on 08.05.2020) | Upto 19.03.2020 25.31% |  |  | During Month(April) |  |  | Upto 08.05.2020 25.31% |  |  |  | 
13 | Overall Financial Progress (as on 08.05.2020) | Upto 31.01.2020 8.74% |  |  | During Month(March) 2.1% |  |  | Upto 08.05.2020 10.84% |  |  |  | 

## Slide 3
Sl. No | Name of the work | Physical Progress of work |  |  |  | Financial Progress in lakh |  |  | Scheduled date of completion
 |  | Total Qty of Work (KM) | Progress up to 08.05.2020 (KM) | Balance (KM) | % | Total Cost (Lakhs) | Expenditure up to 08.05.2020 (Lakhs) | % | 
I | Collection system |  | work is under Progress |  |  |  |  |  | 
1 | Sewer lines(km) | 209.401 | 69.50 | 139.91 | 25.31 | 37685.74 | 3283.25 | 10.84 | 31.12.2021
2 | Manholes (Nos.) | 8649 | 4100 | 4549 |  |  |  |  | 
3 | House Service Connection (Nos.) | 43270 | 4428 | 38842 |  |  |  |  | 
4 | Pumping station | 5 | 1 No PCC work completed. And fabrication work in progress 1No.PCC work in progress 2 Nos. Earth Work under Progress | 2 |  |  |  |  | 
5 | Lifting station | 7 | 2 No. Earth Work under Progress | 4 |  |  |  |  | 
6 | Pumping Main(km) | 14.430 | 0.245 | 14.185 |  |  |  |  | 
7 | Road Restoration(Km) | 223.831 | 9.79km | 214.041 |  |  |  |  | 
8 | Pipe caring Bridge (650m) | 1 No. | Nil | 1 No. |  |  |  |  | 
9 | Sewage Treatment Plant – 50 mld (DBOT Method) | 1 No. | PCC work completed Fabrication work in progress | 1 No. |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-II - Abstract

## Slide 4
Sl. No | Name of the work | Physical Progress of work |  |  |  | Financial Progress in lakh |  |  | Scheduled date of completion
 |  | Total Qty of Work (KM) | Progress up to 08.05.2020 (KM) | Balance (KM) | % | Total Cost | Expenditure up to 08.05.2020 (Lakhs) | % | 
I | Collection system |  | work is under Progress |  |  |  |  |  | 
1 | Sewer lines(km) | 116.282 | 43.70 | 75.411 | 29.83 | 14373.40 | 1916.50 | 13.33 | 31.12.2021
2 | Manholes (Nos.) | 4719 | 2405 | 2467 |  |  |  |  | 
3 | House Service Connection (Nos.) | 21202 | 3211 | 18377 |  |  |  |  | 
4 | Pumping station(Nos.) | 3 | 1 No PCC work completed. And fabrication work in progress 1 No. PCC work in progress 1 Nos. Earth Work under Progress | 0 |  |  |  |  | 
5 | Lifting station(Nos.) | 1 | 1 No. Earth Work under Progress | 1 |  |  |  |  | 
6 | Pump set(Nos.) | 11 | Nil | 11 |  |  |  |  | 
7 | Pumping Main(km) | 8.145 | 0.245 | 7.9 |  |  |  |  | 
8 | Road Restoration (Km) | 124.427 | 5.30 | 122.381 |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-II –Package-1 - Abstract

## Slide 5
Sl. No | Name of the work | Physical Progress of work |  |  |  | Financial Progress in lakh |  |  | Scheduled date of completion
 |  | Total Qty of Work (KM) | Progress up to 08.05.2020 (KM) | Balance (KM) | % | Total Cost | Expenditure up to 08.05.2020 (Lakhs) | % | 
I | Collection system |  | work is under Progress |  |  |  |  |  | 
1 | Sewer lines(km) | 93.119 | 25.80 | 69.399 | 19.59 | 16341.34 | 1366.82 | 8.36 | 31.12.2021
2 | Manholes (Nos.) | 3930 | 1695 | 2319 |  |  |  |  | 
3 | House Service Connection (Nos.) | 22068 | 1217 | 21021 |  |  |  |  | 
4 | Pumping station(Nos.) | 2 | 1 No Earth work in progress. | 1 |  |  |  |  | 
5 | Lifting station(Nos.) | 6 | 2 No Earth work in progress | 4 |  |  |  |  | 
6 | Pump set(Nos.) | 21 | Nil | 21 |  |  |  |  | 
7 | Pumping Main(km) | 6.285 | Nil | 6.285 |  |  |  |  | 
8 | Pipe caring Bridge (650m) | 1 No. | Nil | 1 No. |  |  |  |  | 
9 | Road Restoration (Km) | 99.404 | 4.50 | 94.904 |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-II –Package-2 - Abstract

## Slide 6
Sl. No | Name of the work | Physical Progress of work |  |  | Financial Progress in lakh |  |  | Scheduled date of completion
 |  | Total Item No | Progress up to 08.05.2020 (%) | Balance Item % | Total Cost (Lakhs) | Expenditure up to 08.05.2020 (Lakhs) | % | 
I | Construction Of STP | 100% | 2% | 98% |  |  |  | 
 | Capacity : 50MLD |  |  |  |  |  |  | 
 | Technology : SBR |  |  |  |  |  |  | 
1 | Inlet Chamber | 1 |  |  | 6971.00 | Nil | Nil | 31.12.2020
2 | Screen Chamber | 6 |  |  |  |  |  | 
3 | Detritor | 2 |  |  |  |  |  | 
4 | Parshall flume | 1 |  |  |  |  |  | 
5 | SBR Tank | 4 | PCC work completed. Fabrication work in progress | 1.20 |  |  |  | 
6 | Air Blower Rooms | 1 |  |  |  |  |  | 
7 | UV Channel | 1 |  |  |  |  |  | 
8 | Treated effluent sump | 1 |  |  |  |  |  | 
9 | Outlet pipe | 2.4km |  |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-II –Package-3 - Abstract

## Slide 7
I | Construction Of STP |  |  |  |  |  |  | 
10 | Sludge sump | 2 |  |  | Nil | Nil | Nil | 31.12.2020
11 | Filter press building | 1 |  |  |  |  |  | 
12 | Filter press feed pump house | 1 |  |  |  |  |  | 
13 | Screw Pump / Blower House | 1 |  |  |  |  |  | 
14 | PLcc, DG, Main Pannel & Transformar Room | 1 |  |  |  |  |  | 
15 | Road Works | 1 |  |  |  |  |  | 
16 | Strom Water Drains | 1 |  |  |  |  |  | 
17 | Path ways | 1 |  |  |  |  |  | 
18 | Administration & Lab Buildings | 1 |  |  |  |  |  | 
19 | Landscaping | 1 |  |  |  |  |  | 
20 | Security Cabin | 1 |  |  |  |  |  | 
21 | Staff Quarters | 1 |  |  |  |  |  | 
22 | Compound wall | 1 |  |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-II –Package-3 - Abstract

## Slide 8
PACKAGE – 3 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
Sl. No. | Name of the Agency | Total Nos. | Obtained | Balance | Permitting Authority | Details of Permission requested | Date of application | Present Stage | Probable date of obtaining permission | Remarks (Chronological events to be specified)
1 | NHAI Crossings | - | - | - | - | - | - | - | - | -
 | NHAI Along the Road | - | - | - | - | - | - |  |  | 
 |  |  |  |  |  |  |  |  | - | 
2 | NATIONAL HIGHWAYS Crossings | - | - | - | - | - | - | - | - | 
 | NATIONAL HIGHWAYS Along the Road | - | - | - | - | - | - |  |  | 
 |  |  |  |  |  |  |  |  | - | 

## Slide 9
PACKAGE – 3 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
3 | STATE HIGHWAYS Along the Road & Crossings | 2.00 Km | - | 2.00 Km | ADE Katpadi Vellore | SH 59 in between Dhandapani Kalyana Mandabam to VG Rao Nagar Junction | 11.04.2019 | Approved awaited | 31.07.2020 | 
4 | CLA |  |  |  |  |  |  |  |  | 
5 | PWD | 1 No | - | 1No | EE Irrigation PWD Vellore | Pandian Channel in VG Rao Nagar | 30.04.2019 | - | 31.07.2020 | 
6 | HR & CE DEPARTMENT | - | - | - | - | - | - | - | - | 
7 | FOREST DEPT | - | - | - | - | - | - | - | - | 
8 | REVENUE |  |  |  |  |  |  |  |  | 
9 | RAILWAYS | - | - | - | - | - | - |  | - | 
10 | TNEB –LT | - | - | - | - | - | - | - |  | 
11 | TNPCB | 1No | --- | 1No | DEE Katpadi Vellore | Construction of STP of Capacity 50MLD at Viruthampattu | 10.05.2019 Resubmitted on11.06.2019 after awaiting his remarks | - | - | 

## Slide 10
Sl. No. | Name of Component | Quantity (Km) | Completed (Km) | Balance (Km) | Date of completion
 | Physical Progress - Package 1 |  |  |  | 
I | Collection system |  | Supply / laid | Supply / laid | 
1 | Sewer lines ( Km) | 116.282 | work is under Progress |  | 31.12.2021
 | UPVC Pipe (200mm) | 90.112 | 72.726 / 40.600 | 17.386 / 49.512 | 
 | CI Pipe (350 to 700mm) | 9.061 | 0.698 / 0 | 8.363 / 9.061 | 
 | DWC Pipe (200 to 300mm) | 17.109 | 11.334 / 0.271 | 5.775 / 16.838 | 
 | Total | 116.282 | 84.758/ 40.871 | 31.524/ 75.411 | 
2 | Manholes (Nos.) | 4719 |  |  | 31.12.2021
 | Brick work | 3531 | 2252 | 1279 | 
 | RCC | 1188 | 0 | 1188 | 
 | Total | 4719 | 2252 | 2467 | 
3 | HSC (Nos.) 21202 Nos, 127.212km | 21202 Nos 254.424 Km | 2825 Nos. 100.002 / 23.400 | 18446 Nos. 154.422 / 231.024 | 31.12.2021
4 | Pumping Main (Km) | 8.145 | 1.400/0.000 | 6.745/ 8.145 | 31.12.2021
5 | Road Restoration (Km) | 124.427 | 2.046 | 122.381 | 31.12.2021
UGSS to Vellore City Corporation Package - 1

## Slide 11
Sl. No. | Name of Component | Quantity | Completed | Balance | Date of completion | Action Plan |  |  |  | 
 |  |  |  |  |  | Target | Achievement | Target | Target | Target
II | Lift station – 1 Nos |  |  |  | 1 No. Earth work under progress |  |  |  |  | 
i | Pump set (Nos) | 2 | - | 2 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 0.545 | - | 0.545 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 1 | - | 1 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 1 | - | 1 |  | -- | -- | -- | -- | --
III | Pumping Station – 3 Nos |  |  |  | SPS -4 PCC work completed and fabrication in progress and SPS – 3 & 5 Earth Work Under Progress |  |  |  |  | 
i | Pump set (Nos) | 9 | - | 9 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 7.600 | - | 7.600 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 3 | - | 3 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 3 | - | 3 |  | -- | -- | -- | -- | --

## Slide 12
PACKAGE –1 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
Sl. No. | Name of the Agency | Total Nos. | Obtained | Balance | Permitting Authority | Details of Permission requested | Date of application | Present Stage | Probable date of obtaining permission | Remarks (Chronological events to be specified)
1 | NHAI Crossings | 5 | - | 5 | PD NHAI Krishnakiri | NH48-In between Green circle and Alamelumangapuram as Five location | 11.04.2019 | Preparation of revised drawing as per the P.O letter No NHAI/11013/743 Date 30.04.2019 as per Guidelines is in Progress | 30.10.2020 | -
 | NHAI Along the Road | 3 | - | 3 | PD NHAI Krishnakiri | NH48-In between Green circle to Alamelumangapuram for 1.37 Km in Three location | 11.04.2019 | Preparation of revised drawing as per the P.O letter No NHAI/11013/743 Date 30.04.2019 as per Guidelines is in Progress | 31.10.2020 | 
2 | NATIONAL HIGHWAYS Crossings | - | - | - |  |  |  |  |  | 
 | NATIONAL HIGHWAYS Along the Road | - | - | - |  |  |  |  |  | 

## Slide 13
PACKAGE –1 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
3 | STATE HIGHWAYS Along the Road & Crossings | - | - | - |  |  |  |  |  | 
4 | CLA | - | - | - | - |  |  |  |  | 
5 | PWD | - | - | - | - |  |  |  |  | 
6 | HR & CE DEPARTMENT | - | - | - | - |  |  |  |  | 
7 | FOREST DEPT | - | - | - | - |  |  |  |  | 
8 | REVENUE | - | - | - | - |  |  |  |  | 
9 | RAILWAYS | - | - | - | - |  |  |  |  | 
10 | TNEB –LT | --- | --- | --- | --- | --- |  |  |  | 

## Slide 14
Sl. No. | Name of Component | Quantity (Km) | Completed (Km) | Balance (Km) | Date of completion
 | Physical Progress - Package 2 |  |  |  | 
I | Collection system |  | Supply / laid | Supply / laid | 
1 | Sewer lines ( Km) | 93.119 | work is under Progress |  | 31.12.2021
 | UPVC Pipe (200mm) | 64.212 | 47.430 / 25.246 | 16.782 / 38.966 | 
 | CI Pipe (350 to 700mm) | 10.517 | 1.302 / 0 | 9.215 / 10.517 | 
 | DWC Pipe (200 to 300mm) | 18.390 | 7.974 / 0.553 | 10.416 / 17.837 | 
 | Total | 93.119 | 48.666 / 23.720 | 44.453/ 69.399 | 
2 | Manholes (Nos.) | 3930 |  |  | 31.12.2021
 | Brick work | 2799 | 1611 | 1188 | 
 | RCC | 1131 | 0 | 1131 | 
 | Total | 3930 | 1611 | 2319 | 
3 | HSC (Nos.) 22068 Nos. 132.408km | 22068 Nos. 264.816km | 1047 Nos 57.558 / 12.100 | 21021 Nos. 207.258 / 252.716 | 31.12.2021
4 | Pumping Main (Km) | 6.285 | - | 6.285 | 31.12.2021
5 | Road Restoration (Km) | 99.404 | 4.500 | 94.904 | 31.12.2021
UGSS to Vellore City Corporation Package - 2

## Slide 15
Sl. No. | Name of Component | Quantity | Completed | Balance | Date of completion | Action Plan |  |  |  | 
 |  |  |  |  |  | Target | Achievement | Target | Target | Target
II | Lift station – 6 Nos |  |  |  | 1 No. Concrete work in progress |  |  |  |  | 
i | Pump set (Nos) | 12 | - | 12 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 1.390 | - | 1.390 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 6 | - | 6 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 6 | - | 6 |  | -- | -- | -- | -- | --
III | Pumping Station – 2 Nos |  |  |  | 1 No. Earth work under progress |  |  |  |  | 
i | Pump set (Nos) | 9 | - | 9 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 4.895 | - | 4.895 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 2 | - | 2 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 2 | - | 2 |  | -- | -- | -- | -- | --

## Slide 16
PACKAGE –2 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
Sl. No. | Name of the Agency | Total Nos. | Obtained | Balance | Permitting Authority | Details of Permission requested | Date of application | Present Stage | Probable date of obtaining permission | Remarks (Chronological events to be specified)
1 | NHAI Crossings | 1 | - | 1 | PD NHAI Krishnagiri | NH48 AT Shanpakkam | 11.04.2019 | Preparation of revised drawing as per the P.O letter No NHAI/11013/743 Date 30.04.2019 as per Guidelines is in Progress | 31.10.2020 | 
 | NHAI Along the Road | 1 | - | 1 | PD NHAI Krishnagiri | NH48 AT Shanpakkam for 480m | 11.04.2019 | Preparation of revised drawing as per the P.O letter No NHAI/11013/743 Date 30.04.2019 as per Guidelines is in Progress | 31.10.2020 | 
2 | NATIONAL HIGHWAYS Crossings | 2 | - | 2 |  | 1.Sainathapuram Nalla 2.Virupachapuram near School |  |  |  | 
 | NATIONAL HIGHWAYS Along the Road | 2 No for 2.20Km | - | 2 No | ADE Vellore | 1. NH 38 in between Sainathapuram and valpadi an 1.00Km 2.NH 38 near Koil to Bishop Dvaid Nagar 1.20Km | 11.04.2019 | Preparation of revised drawing as per ADE Vellore letter No 20/2019 Date 18.04.2019 as per Guidelines is in Progress | 31.08.2020 | 

## Slide 17
PACKAGE –2 UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
3 | STATE HIGHWAYS a)Along the Road & b) Crossings | 1No 1Km | - | 1No 1Km | ADE Katpadi Vellore | SH-207 1No 1Km in between Baby Residency to Tollgate | 11.04.2019 | Preparation of received drawing as per instruction of the ADE is in Progress | 31.08.2020 | 
 |  | 3No | - | 3No | ADE Katpadi Vellore | SH-207 3No in between Anna Nagar Main Road and Virupatchipuram | 11.04.2019 |  |  | 
4 | CLA | - | - | - |  |  |  |  |  | 
5 | PWD | 1 | - | 1 | EE PWD Irrigation Vellore | Across Palar River for a laying of 570m for pipe carrying Bridge | 11.04.2019 | Approval awaited from the EE | 31.08.2020 | 
6 | HR & CE DEPARTMENT |  |  |  |  |  |  |  |  | 
7 | FOREST DEPT |  |  |  |  |  |  |  |  | 
8 | REVENUE |  |  |  |  |  |  |  |  | 
9 | RAILWAYS Crossing | 4 | - | 4 | Divesional Manager Trichy | Crossing in between Chinna Allpuram and Venkatapuram | 11.04.2019 | Approval Awaited | 31.08.2020 | 
10 | TNEB –LT | --- | --- | --- | --- | --- |  |  |  | 
11 | ASI | 10.193 KM 1No | - | 10.193 KM 1No | Superindenting Archaeologist, St.George , Fort Chennai-18 | Burma Colony Near Vellore Fort | 16.04.2019 | Joint Inspection by ASI on 04.06.2019 | 31.08.2020 | 

## Slide 18
x | Name of Scheme | AMRUT – 2016-17 UGSS TO Vellore City Municipal Corporation – Phase III |  |  |  |  |  |  |  | 
1. | Population and Requirement | Population Benefited (in Lakhs) |  |  |  |  |  |  | Sewage in MLD | 
 |  | Present (2020) |  | Inter (2035) |  |  | Ultimate (2050) |  | Inter (2035) | Ultimate (2050)
 |  | 1.88 |  | 2.59 |  |  | 3.53 |  | 28.53 | 38.84
2 | Administrative Sanction with amount | G.O. (Ms) No. 5 /MA&WS (MA2) dept., dt. 22.01.2018 For Rs. 29377.00 Lakh |  |  |  |  |  |  |  | 
3 | Technical Sanction with amount | Roc.No No. 4659/ 2018 /DO1 Date. 29.05.2018 For Rs. 30500.00 Lakh , The Chief Engineer, O/o the Commissioner of Municipal Administration, Chennai |  |  |  |  |  |  |  | 
4 | Date of Work Order | Technical Evaluation report placed before ADB for NOC .Tender Award Committee Approved on 29.01.2019. Revised PBER ADB through TNUIFSL for Final NOC on 01-02-2019. LOA Issued on 14.02.2019,Work order issued on 04.03.2019. |  |  |  |  |  |  |  | 
5 | Agreement No. /date / Value & Period | Agreement No: 4/2018-19 dt 04.03.2019 Rs. 299,92,42,000.00. 36 Month |  |  |  |  |  |  |  | 
6 | Date of Commencement | 04.03.2019 |  |  |  |  |  |  |  | 
7 | Name of the Contractor | M/S Larsen Toubro Limited, Chennai. |  |  |  |  |  |  |  | 
8 | Target date for completion | 31.03.2022 |  |  |  |  |  |  |  | 
9 | Expected date for completion | 31.03.2022 |  |  |  |  |  |  |  | 
11 | Description | Grant GOI Cr | GOTN (Cr) |  |  | Own fund (ULB) |  | ADB/TUFIDCO/ TNUIFSL loan |  | Total
 | Fund Tie up | 124.13 | 49.65 |  |  | 29.38 |  | 90.61 |  | 293.77 cr
 | Funds Received | -- | -- |  |  | -- |  | -- |  | --
 | Balance to be received | -- | -- |  |  | -- |  | -- |  | --
 | Budget 2018-19 |  |  |  |  |  |  |  |  | 
 | Expenditure incurred up to 31.03.2019 | 1499.62 Lakhs |  |  |  |  |  |  |  | 
 | Expenditure during 2019-20,2020-2021 | 4557.85 Lakhs & 484.70 Lakhs |  |  |  |  |  |  |  | 
 | Cumulative Expenditure as on 08.05.2020 | 6542.37 Lakhs |  |  |  |  |  |  |  | 
12 | Overall Physical Progress (as on 08.05.2020) | Upto 31.03.2020 20.15% |  |  | During this week - |  |  | Upto 08.05.2020 20.15% |  | 
13 | Overall Financial Progress (as on 08.05.2020) | Upto 31.03.2020 20.20% |  |  | During this week 1.61% |  |  | Upto 08.05.2020 21.81% |  | 

## Slide 19
Sl. No | Name of the work | Physical Progress of work |  |  |  | Financial Progress in lakh |  |  | Scheduled date of completion
 |  | Total Qty of Work (KM) | Progress up to 08.05.2020 (KM) | Balance (KM) | % | Total Cost (Lakhs) | Expenditure up to 08.05.2020 (Lakhs) | % | 
I | Collection system |  | work is under Progress |  |  |  |  |  | 
1 | Sewer lines(km) | 281.164 | 52.65 | 228.51 | 20.15 | 29992.42 | 6542.37 | 21.81% | 31.03.2022
2 | Manholes (Nos.) | 11494 | 2409 | 9085 |  |  |  |  | 
3 | House Service Connection (Nos.) | 28200 | 518 | 27682 |  |  |  |  | 
4 | Pumping station(Nos) | 3 | 1 No. Earth work under progress | 2 |  |  |  |  | 
5 | Lifting station(Nos) | 5 | 2 No. Earth work in Progress | 3 |  |  |  |  | 
6 | Pumping Main(km) | 6.965 | Nil | 6.965 |  |  |  |  | 
7 | Road Restoration(Km) | 288.129 | 8.705 | 279.42 |  |  |  |  | 
AMRUT 2016-17 UGSS TO Vellore City Municipal Corporation - Phase-III - Abstract

## Slide 20
Sl. No. | Name of Component | Quantity (Km) | Completed (Km) | Balance (Km) | Date of completion
 | Physical Progress - Package 1 |  |  |  | 
I | Collection system | work is under Progress | Supply / laid | Supply / laid | 
1 | Sewer lines ( Km) | 281.164 |  |  | 31.03.2022
 | UPVC Pipe (200mm) | 216.666 | 100.00/ 31.840 | 116.666 / 184.826 | 
 | CI Pipe (350 to 700mm) | 17.965 | 13.113 / 0.100 | 4.582 / 17.865 | 
 | DWC Pipe (200 to 300mm) | 46.533 | 46.533 / 1.080 | 0.00 / 45.453 | 
 | Total | 281.164 | 159.646/33.020 | 121.518/248.144 | 
2 | Manholes (Nos.) | 11494 |  |  | 31.03.2022
 | Brick work | 8373 | 1943 | 6430 | 
 | RCC | 3121 | 0 | 3121 | 
 | Total | 11494 | 1943 | 9551 | 
3 | HSC (Nos.) (28200 Nos – 169.200) | 28200 Nos. 338.400 km | 220 Nos. 120.000 / 1.320 | 27980 Nos 218.40km/337.080 | 31.03.2022
4 | Pumping Main (Km) | 6.965 | 1.320 / 0.00 | 5.645 / 0.00 | 31.03.2022
5 | Road Restoration (Km) | 288.129 | 0.780 | 287.349 | 31.03.2022
UGSS to Vellore City Corporation Phase – III

## Slide 21
Sl. No. | Name of Component | Quantity | Completed | Balance | Date of completion | Action Plan |  |  |  | 
 |  |  |  |  |  | Target | Achievement | Target | Target | Target
II | Lift station – 5 Nos |  |  |  | 2 No. Earth work under progress |  |  |  |  | 
i | Pump set (Nos) | 10 | - | 10 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 0.755 | - | 0.755 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 5 | - | 5 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 5 | - | 5 |  | -- | -- | -- | -- | --
III | Pumping Station – 3 Nos |  |  |  | Leveling work under progress |  |  |  |  | 
i | Pump set (Nos) | 9 | - | 9 |  | -- | -- | -- | -- | --
ii | Pumping main (Km) | 6.210 | - | 6.210 |  | -- | -- | -- | -- | --
iii | Pump room (Nos) | 3 | - | 3 |  | -- | -- | -- | -- | --
iv | Status of Power supply (LT/HT Fourth wire /SFM (Nos) | 3 | - | 3 |  | -- | -- | -- | -- | --

## Slide 22
Phase-III UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT - ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
Sl. No. | Name of the Agency | Total Nos. | Obtained | Balance | Permitting Authority | Details of Permission requested | Date of application | Present Stage | Probable date of obtaining permission | Remarks (Chronological events to be specified)
1 | NHAI Crossings |  |  |  |  |  |  |  |  | 
 | NHAI Along the Road |  |  |  |  |  |  |  |  | 
2 | NATIONAL HIGHWAYS Crossings | 1 | - | 1 | ADE Vellore | Virupachapuram | 11.04.2019 | ADE Vellore in between this site Approved Awaited -do- |  | 
 | NATIONAL HIGHWAYS Along the Road | 6.367 km | - | 6.367 km | ADE Vellore | NH 38 for 3.540 km in between Virupachipuram and Edayanchattu NH 75 2.827 km in between cChitoor busstand and Viruthampattu | 11.04.2019 11.04.2019 |  |  | 
 |  |  |  |  |  |  |  |  | 31.08.2020 | 

## Slide 23
Phase-III UGSS SCHEME TO VELLORE MUNICIPAL CORPORATION IN VELLORE DISTRICT ISSUES/PERMISSIONS FROM LINE DEPARTMENTS : |  |  |  |  |  |  |  |  |  | 
 | Issues/Permissions from line Departments : |  |  |  |  |  |  |  |  | 
3 | STATE HIGHWAYS Along the Road Crossings | 7.850 Km 25Nos | - - | 7.850 km 25Nos | ADE Katpadi Vellore | 1.S.H .No.59 inbetween Chittoor Busstand to VIT =2.68km .SH No.207 in between 2.Vellore to Ariyur Golden Temple = 5.12km Chitoor Bus Stand to VIT Thorapadi to Ariyur Golden Temple | 11.04.2019 | Permission awaited | 31.07.2020 | 
4 | CLA |  |  |  |  |  |  |  |  | 
5 | PWD |  |  |  |  |  |  |  |  | 
6 | HR & CE DEPARTMENT |  |  |  |  |  |  |  |  | 
7 | FOREST DEPT |  |  |  |  |  |  |  |  | 
8 | REVENUE |  |  |  |  |  |  |  |  | 
9 | RAILWAYS | 2 |  | 2 | Divisional Manager Chennai | 2Nos at Chainage 127/19 and 127/17 Near VIT | 11.04.2019 | Permission awaited | 31.08.2020 | 
 |  | 2 |  | 2 | Divisional Manager Trichy | (i)At Chainage in between 148/25 128/23 Near Thorapadi (ii)At Chainage 155/3 and 155/4 in between near vanjur 1No |  |  |  | 
10 | TNEB –LT | --- | --- | --- | --- | --- |  |  |  | 
11 | ASI | 0.751 km | - | 0.751 km | Superdenting Aerologist St.George fort house chennai-18 | Vasanthapuram near vellore fort | 16.05.2019 | Jointly inspected on 04.06.2019 Permission awaited | 31.08.2020 |